## Project Planner
Project Planner - Software Engineering Group 15
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  | Plan Duration |  |  | Actual Start |  | % Complete |  | Actual (beyond plan) |  |  | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | Weeks
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Frontend - Boilerplate | 1 | 2 | 1 |  | 10%
Backend - Boilerplate | 1 | 2 |  |  | 0%
Frontend for User Pages | 2 | 4 |  |  | 0%
Frontend for Listings Feed | 4 | 8 |  |  | 0%
Create Early Stage ML Model | 4 | 2 |  |  | 0%
Integrate frontend and Backend | 4 | 3 |  |  | 0%
Test ML Model | 5 | 4 |  |  | 0%
Integrate ML Model with Backend | 5 | 2 |  |  | 0%
Frontend Refinement | 5 | 2 |  |  | 0%
Email authentication | 6 | 5 |  |  | 0%
Integrate DB with Backend | 6 | 1 |  |  | 0%
Design Early RDBMS Schema | 9 | 3 |  |  | 0%
Map View for Listings | 9 | 6 |  |  | 0%
Backend Development | 2 | 8 |  |  | 0%
Test Application With Users | 11 | 3 |  |  | 0%